Backlog

**U7:** As Josh, a TEQ LIP staff, I want to be able to create a customized list of variables to query through the data so I can generate reports with the specific information I need.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T24. | Display the user generated table. | T22, T23 | 5 |

**U8:** As Josh, a TEQ LIP staff, I want to save my previous customized queries to a dashboard from a dropdown menu so I can generate reports with pre-set queries.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T28. | Integrate the API with the frontend. | T25, T27 | 5 |

**U9:** As Charlie, a TEQ LIP staff, I want to be able to use preset queries to query through all the collected anonymized data so that I can generate baseline reports.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T29. | Update front end to allow user to select preset queries. |  | 5 |
| T30. | Write backend API to get the table generated by the preset query. |  | 4 |
| T31. | Integrate the API with the frontend. | T29, T30 | 5 |

Sprint Plan

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| U7 | T24 |  | 5 |  |  | A:5 |  |  |  |  |
| U8 | T28 | T25, T27 | 5 |  |  |  | Z:5 |  |  |  |
| U9 | T29 |  | 5 |  |  | M:5 |  |  |  |  |
|  | T30 |  | 4 |  |  |  |  | D:4 |  |  |
|  | T31 | T29, T30 | 5 |  |  |  |  |  | J:5 |  |
|  |  |  | 24 |  |  |  |  |  |  |  |

Changes

* Michelle completed T29 on Thursday instead of Wednesday
* Zhongyang completed T28 on Saturday instead of Thursday

Sprint Execution

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| U7 | T24 |  | 5 |  | A:4 | A:1 |  |  |  |  |
| U8 | T28 | T25, T27 | 5 |  |  |  |  |  | Z:5 |  |
| U9 | T29 |  | 5 |  |  | M:4 | M:1 |  |  |  |
|  | T30 |  | 4 |  |  |  |  | D:4 |  |  |
|  | T31 | T29, T30 | 5 |  |  |  |  |  | J:5 |  |
|  |  |  | 24 |  |  |  |  |  |  |  |

Burndown Chart

