Backlog

**U10:** As Josh, a TEQ LIP staff, I want to be able to delete data so that I can remove redundant data and keep the data clean and accurate.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T32. | Create frontend to display rows as well as an option to manually delete a row |  | 3 |
| T33. | Write backend API to delete a row |  | 2 |
| T34. | Integrate the frontend with the backend API | T32, T33 | 2 |

**U11:** As Charlie, a TEQ LIP staff, I want to be able to export the queried data into a CSV file for record keeping.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T35. | Add a button to save data to a csv on the frontend for querying the data. |  | 1 |
| T36. | Write backend API that retrieves a csv file from the data. |  | 4 |
| T37. | Integrate the API with the frontend | T35, T36 | 3 |

**U12:** As Amy an administrator at a support agency, I want to be given help throughout the system so that I can easily navigate the system.

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Short Description | Dependency | Story Point |
| T38. | Add a ‘help’ option to the HTML pages |  | 1 |
| T39. | Write jQuery event handlers to display instructions on how to use each page | T38 | 3 |

Sprint Plan

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| U10 | T32 |  | 3 |  |  | J:3 |  |  |  |  |
|  | T33 |  | 2 |  |  |  |  | Z:2 |  |  |
|  | T34 | T32,T33 | 2 |  |  |  |  | Z:2 |  |  |
| U11 | T35 |  | 1 | J:1 |  |  |  |  |  |  |
|  | T36 |  | 4 |  |  | A:4 |  |  |  |  |
|  | T37 |  | 3 |  |  |  | D:3 |  |  |  |
| U12 | T38 |  | 1 |  |  | M:1 |  |  |  |  |
|  | T39 |  | 3 |  |  | M:3 |  |  |  |  |

Changes

* Jonathan completed T32 on Wednesday instead of Tuesday
* Zhongyang completed T33 on Friday instead of Wednesday
* Zhongyang completed T34 on Friday instead of Thursday

Sprint Execution

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| U10 | T32 |  | 3 |  |  | J:3 |  |  |  |  |
|  | T33 |  | 2 |  |  |  |  | Z:2 |  |  |
|  | T34 | T32,T33 | 2 |  |  |  |  | Z:2 |  |  |
| U11 | T35 |  | 1 | J:1 |  |  |  |  |  |  |
|  | T36 |  | 4 |  |  | A:4 |  |  |  |  |
|  | T37 |  | 3 |  |  |  | D:3 |  |  |  |
| U12 | T38 |  | 1 |  |  | M:1 |  |  |  |  |
|  | T39 |  | 3 |  |  | M:3 |  |  |  |  |

Burndown Chart

