## Sprint Plan
User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
U10 | T32 |  | 3 |  | J:3
| T33 |  | 2 |  |  | Z:2
| T34 | T32,T33 | 2 |  |  |  | Z:2
U11 | T35 |  | 1 | J:1
| T36 |  | 4 |  |  | A:4
| T37 |  | 3 |  |  |  | D:3
U12 | T38 |  | 1 |  | M:1
| T39 |  | 3 |  |  | M:3
U13 | T40 |  | 3
| T41 |  | 2
| T42 | T41 | 3
| T43 | T40,T42 | 3
U14 | T44 |  | 2
| T45 |  | 4
| T46 | T44, T45 | 3

## Sprint Execution
User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
U10 | T32 |  | 3
| T33 |  | 2
| T34 | T32,T33 | 2
U11 | T35 |  | 1
| T36 |  | 4
| T37 |  | 3
U12 | T38 |  | 1
| T39 |  | 3
U13 | T40 |  | 3
| T41 |  | 2
| T42 | T41 | 3
| T43 | T40,T42 | 3
U14 | T44 |  | 2
| T45 |  | 4
| T46 | T44, T45 | 3

## Burndown Chart
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Expected | 19 | 18 | 14 | 5 | 0 | 0 | 0 | 0
Actual | 19 | 18