## Sprint Plan
User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
U13 | T40 |  | 3 |  |  | J:3
| T41 |  | 2 |  |  | J:2
| T42 | T41 | 3 | [5 empty] | Z:3
| T43 | T40,T42 | 3 | [6 empty] | M:3
U14 | T44 |  | 2 |  |  | D:2
| T45 |  | 4 |  | A:4
| T46 | T44, T45 | 3 |  |  |  |  | D:3
Additional Tasks
Testing | D
Uploading Data | Anyone
Video | J
Video Editing | A
Video Upload | M
Additional CSS | M
Report | M

## Sprint Execution
User Story | Task | Dependencies | Story Points | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
U13 | T40 |  | 3 |  |  | J:3
| T41 |  | 2 |  |  | J:2
| T42 | T41 | 3 | [5 empty] | Z:3
| T43 | T40,T42 | 3 | [6 empty] | M:3
U14 | T44 |  | 2 |  |  | D:2
| T45 |  | 4 |  | A:4
| T46 | T44, T45 | 3 |  |  | D:3

## Burndown Chart
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Expected | 20 | 20 | 16 | 9 | 9 | 6 | 3 | 0
Actual | 20 | 20 | 16 | 6 | 6 | 6 | 3 | 0